## Foglio1
Daniele Moltisanti
Task name | Start Date | End Date | Hours(h) | Day
Design Document | 2017-11-02 | 2017-11-25 | 21
Brainstorming and general overview | 2017-11-02 | 2017-11-12 | 5 | 11
2. Architectural Design (Overview) | 2017-11-05 | 2017-11-06 | 2 | 2
2. Architectural Design (Component View) | 2017-10-09 | 2017-11-12 | 3.5 | 4
2. Architectural Design (Runtime View) | 2017-10-15 | 2017-11-22 | 4.5 | 8
2. Architectural Design (Component Interface) | 2017-10-16 | 2017-11-24 | 2 | 9
2. Architectural Design (Archetectural style and pattern) | 2017-10-14 | 2017-11-15 | 1 | 2
Final revision | 2017-11-20 | 2017-11-25 | 3 | 6
Andrea Mazzeo
Task name | Start Date | End Date | Hours(h) | Day
Design Document | 2017-11-02 | 2017-11-25 | 23.5
Brainstorming and general overview | 2017-11-02 | 2017-11-12 | 5 | 11
3. Algorithm Design | 2017-11-04 | 2017-11-09 | 6 | 6
4. User Interface Design | 2017-11-06 | 2017-11-14 | 4 | 10
1. Introduction | 2017-11-23 | 2017-11-24 | 1 | 2
Latex | 2017-11-16 | 2017-11-25 | 4.5 | 10
Final revision | 2017-11-20 | 2017-11-25 | 3 | 6
Andrea Mafessoni
Task name | Start Date | End Date | Hours(h) | Day
Design Document | 2017-11-02 | 2017-11-25 | 19.5
Brainstorming and general overview | 2017-11-02 | 2017-11-12 | 5 | 11
2. Architectural Design (Deployment View) | 2017-11-12 | 2017-11-14 | 4 | 3
5. Requirements Traceability | 2017-11-22 | 2017-11-24 | 3.5 | 3
6. Implementation, Integration and Test Plan | 2017-11-16 | 2017-11-21 | 4 | 6
Final revision | 2017-11-20 | 2017-11-25 | 3 | 6

## Foglio2
November
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | Andrea Mazzeo
DD
Brainstorming and general overview
3. Algorithm Design
4. User Interface Design
1, Introduction
Latex
Final Revision